## DCCS
| Date | 2022-03-02
| Well | GK-W526C
| USDMYR | 4.5
| Daily Cost | 16500
File Name | OCS Number | Well Name | WBS Number | AFE Number | Cost Group | Description | Daily Estimate (USD) | SAP Unit Price | Currency | Unit of Measure | Charging Mechanism | Total Cost (USD) | Total Units | time axis 2022-03-02 to 2022-07-02
OCS_1.xlsx | OCS -001/(8) Drilling Fluids - F14 | GK-W526C | C.MY.F14.DD.22.001.1094D | 30318813 | 15 | Description 1 | 0 | 1000 | MYR | unit | 1 unit/day from start phase 50 to end phase 50 for maximum 7 occurrences | 888.8889 | 4 | bar: 2022-05-14 to 2022-05-17
OCS_1.xlsx | OCS -001/(8) Drilling Fluids - F14 | GK-W526C | C.MY.F14.DD.22.001.1094D | 30318813 | 15 | Description 2 | 0 | 1500 | USD | unit | 1.3 unit/day from 2022/04/01 to end phase 50 | 17042.1875 | 11.3615 | 2022-05-09: 0.96146; 2022-05-10: 1.3; 2022-05-11: 1.3; 2022-05-12: 1.3; 2022-05-13: 1.3; 2022-05-14: 1.3; 2022-05-15: 1.3; 2022-05-16: 1.3; 2022-05-17: 1.3
OCS_1.xlsx | OCS -001/(8) Drilling Fluids - F14 | GK-W526C | C.MY.F14.DD.22.001.1094D | 30318813 | 15 | Description 3 | 0 | 5000 | USD | unit | 1.4 unit/day from 2022/04/01 to 2022/05/02 for maximum 7 occurrences | 0 | 0
OCS_1.xlsx | OCS -001/(8) Drilling Fluids - F14 | GK-W526C | C.MY.F14.DD.22.001.1094D | 30318813 | 20 | Description 4 | 14437.5 | 10000 | USD | unit | 2.1 unit/day for {'GK-P527B': [5,10,15,20], 'GK-W526C':[5]} for maximum 15 occurrences | 111562.5 | 11.1562 | 2022-03-02: 1.4438; 2022-03-03: 1.05; 2022-03-13: 1.0719; 2022-03-14: 2.1; 2022-03-15: 2.1; 2022-03-16: 2.1; 2022-03-17: 1.2906
OCS_2.xlsx | OCS -002/(8) Drilling Fluids - F14 | GK-P527B | C.MY.F14.DD.22.001.2094D | 30318813 | 15 | Description 5 | 0 | 1000 | USD | unit | 1 unit/day from start phase 50 to end phase 50 for maximum 7 occurrences | 3000 | 3 | bar: 2022-03-28 to 2022-03-30
OCS_2.xlsx | OCS -002/(8) Drilling Fluids - F14 | GK-P527B | C.MY.F14.DD.22.001.2094D | 30318813 | 15 | Description 6 | 0 | 1500 | USD | unit | 1 unit/day from start phase 15 to end phase 15 for maximum 7 occurrences | 3000 | 2 | bar: 2022-03-16 to 2022-03-17
OCS_2.xlsx | OCS -002/(8) Drilling Fluids - F14 | GK-P527B | C.MY.F14.DD.22.001.2094D | 30318813 | 15 | Description 7 | 0 | 5000 | USD | unit | 1 unit/day from start phase 5 to end phase 50 for maximum 4 occurrences | 20000 | 4 | 2022-03-13: 0.052083; 2022-03-14: 1; 2022-03-15: 1; 2022-03-16: 1; 2022-03-17: 0.94792
OCS_2.xlsx | OCS -002/(8) Drilling Fluids - F14 | GK-P527B | C.MY.F14.DD.22.001.2094D | 30318813 | 20 | Description 8 | 0 | 10000 | USD | unit | 1 unit/day from start phase 20 to end phase 20 for maximum 7 occurrences | 10000 | 1 | bar: 2022-03-17
OCS_3.xlsx | Tariff - Rig Operating Expenses | GK-P527B | C.MY.F14.DD.22.001.2094R | 30318813 | 15 | Description 9 / GK-P527B / C.MY.F14.DD.22.001.2094R | 0 | 1000 | USD | unit | 1 unit/day from 2020/01/01 to 2030/01/01 | 458.3333 | 0.45833 | 2022-03-13: 0.45833
OCS_3.xlsx | Tariff - Rig Operating Expenses | GK-P527B | C.MY.F14.DD.22.001.2094D | 30318813 | 15 | Description 9 / GK-P527B / C.MY.F14.DD.22.001.2094D | 0 | 1000 | USD | unit | 1 unit/day from 2020/01/01 to 2030/01/01 | 19052.0833 | 19.0521 | 2022-03-13: 0.052083; 2022-03-14: 1; 2022-03-15: 1; 2022-03-16: 1; 2022-03-17: 1; 2022-03-18: 0.64583; 2022-03-21: 0.11458; 2022-03-22: 1; 2022-03-23: 1; 2022-03-24: 1; 2022-03-25: 1; 2022-03-26: 1; 2022-03-27: 1; 2022-03-28: 1; 2022-03-29: 1; 2022-03-30: 1; 2022-03-31: 1; 2022-04-01: 1; 2022-04-02: 1; 2022-04-03: 1; 2022-04-04: 1; 2022-04-05: 0.23958
OCS_3.xlsx | Tariff - Rig Operating Expenses | GK-P527B | C.MY.F14.DD.22.001.2094C | 30318813 | 15 | Description 9 / GK-P527B / C.MY.F14.DD.22.001.2094C | 0 | 1000 | USD | unit | 1 unit/day from 2020/01/01 to 2030/01/01 | 8437.5 | 8.4375 | 2022-04-05: 0.76042; 2022-04-06: 1; 2022-04-07: 1; 2022-04-08: 1; 2022-04-09: 1; 2022-04-10: 1; 2022-04-11: 1; 2022-04-12: 1; 2022-04-13: 0.67708
OCS_3.xlsx | Tariff - Rig Operating Expenses | GK-P528C | C.MY.F14.DD.22.001.3094R | 30318813 | 15 | Description 9 / GK-P528C / C.MY.F14.DD.22.001.3094R | 0 | 1000 | USD | unit | 1 unit/day from 2020/01/01 to 2030/01/01 | 20.8333 | 0.020833 | 2022-03-07: 0.020833
OCS_3.xlsx | Tariff - Rig Operating Expenses | GK-P528C | C.MY.F14.DD.22.001.3094D | 30318813 | 15 | Description 9 / GK-P528C / C.MY.F14.DD.22.001.3094D | 0 | 1000 | USD | unit | 1 unit/day from 2020/01/01 to 2030/01/01 | 18562.5 | 18.5625 | 2022-03-07: 0.67708; 2022-03-18: 0.35417; 2022-03-19: 1; 2022-03-20: 1; 2022-03-21: 0.88542; 2022-04-13: 0.32292; 2022-04-14: 1; 2022-04-15: 1; 2022-04-16: 1; 2022-04-17: 1; 2022-04-18: 1; 2022-04-19: 1; 2022-04-20: 1; 2022-04-21: 1; 2022-04-22: 1; 2022-04-23: 1; 2022-04-24: 1; 2022-04-25: 1; 2022-04-26: 1; 2022-04-27: 1; 2022-04-28: 0.32292
OCS_3.xlsx | Tariff - Rig Operating Expenses | GK-P528C | C.MY.F14.DD.22.001.3094C | 30318813 | 15 | Description 9 / GK-P528C / C.MY.F14.DD.22.001.3094C | 0 | 1000 | USD | unit | 1 unit/day from 2020/01/01 to 2030/01/01 | 10937.5 | 10.9375 | 2022-04-28: 0.67708; 2022-04-29: 1; 2022-04-30: 1; 2022-05-01: 1; 2022-05-02: 1; 2022-05-03: 1; 2022-05-04: 1; 2022-05-05: 1; 2022-05-06: 1; 2022-05-07: 1; 2022-05-08: 1; 2022-05-09: 0.26042
OCS_3.xlsx | Tariff - Rig Operating Expenses | GK-W526C | C.MY.F14.DD.22.001.1094R | 30318813 | 15 | Description 9 / GK-W526C / C.MY.F14.DD.22.001.1094R | 687.5 | 1000 | USD | unit | 1 unit/day from 2020/01/01 to 2030/01/01 | 6562.5 | 6.5625 | 2022-03-02: 0.6875; 2022-03-03: 0.5; 2022-06-27: 1; 2022-06-28: 1; 2022-06-29: 1; 2022-06-30: 1; 2022-07-01: 1; 2022-07-02: 0.375
OCS_3.xlsx | Tariff - Rig Operating Expenses | GK-W526C | C.MY.F14.DD.22.001.1094D | 30318813 | 15 | Description 9 / GK-W526C / C.MY.F14.DD.22.001.1094D | 0 | 1000 | USD | unit | 1 unit/day from 2020/01/01 to 2030/01/01 | 19854.1667 | 19.8542 | 2022-03-03: 0.5; 2022-03-04: 1; 2022-03-05: 1; 2022-03-06: 1; 2022-03-07: 0.30208; 2022-05-09: 0.73958; 2022-05-10: 1; 2022-05-11: 1; 2022-05-12: 1; 2022-05-13: 1; 2022-05-14: 1; 2022-05-15: 1; 2022-05-16: 1; 2022-05-17: 1; 2022-05-18: 1; 2022-05-19: 1; 2022-05-20: 1; 2022-05-21: 0.34375; 2022-06-12: 0.14583; 2022-06-13: 1; 2022-06-14: 1; 2022-06-15: 1; 2022-06-16: 0.82292
OCS_3.xlsx | Tariff - Rig Operating Expenses | GK-W526C | C.MY.F14.DD.22.001.1094C | 30318813 | 15 | Description 9 / GK-W526C / C.MY.F14.DD.22.001.1094C | 0 | 1000 | USD | unit | 1 unit/day from 2020/01/01 to 2030/01/01 | 10177.0833 | 10.1771 | 2022-06-16: 0.17708; 2022-06-17: 1; 2022-06-18: 1; 2022-06-19: 1; 2022-06-20: 1; 2022-06-21: 1; 2022-06-22: 1; 2022-06-23: 1; 2022-06-24: 1; 2022-06-25: 1; 2022-06-26: 1
OCS_3.xlsx | Tariff - Rig Operating Expenses | GK-W721C | C.MY.F14.DD.22.001.4094R | 30318813 | 15 | Description 9 / GK-W721C / C.MY.F14.DD.22.001.4094R | 0 | 1000 | USD | unit | 1 unit/day from 2020/01/01 to 2030/01/01 | 41.6667 | 0.041667 | 2022-03-08: 0.041667
OCS_3.xlsx | Tariff - Rig Operating Expenses | GK-W721C | C.MY.F14.DD.22.001.4094D | 30318813 | 15 | Description 9 / GK-W721C / C.MY.F14.DD.22.001.4094D | 0 | 1000 | USD | unit | 1 unit/day from 2020/01/01 to 2030/01/01 | 19145.8333 | 19.1458 | 2022-03-08: 0.95833; 2022-03-09: 1; 2022-03-10: 1; 2022-03-11: 1; 2022-03-12: 1; 2022-03-13: 0.48958; 2022-05-21: 0.65625; 2022-05-22: 1; 2022-05-23: 1; 2022-05-24: 1; 2022-05-25: 1; 2022-05-26: 1; 2022-05-27: 1; 2022-05-28: 1; 2022-05-29: 1; 2022-05-30: 1; 2022-05-31: 1; 2022-06-01: 1; 2022-06-02: 1; 2022-06-03: 1; 2022-06-04: 0.041667
OCS_3.xlsx | Tariff - Rig Operating Expenses | GK-W721C | C.MY.F14.DD.22.001.4094C | 30318813 | 15 | Description 9 / GK-W721C / C.MY.F14.DD.22.001.4094C | 0 | 1000 | USD | unit | 1 unit/day from 2020/01/01 to 2030/01/01 | 8812.5 | 8.8125 | 2022-06-04: 0.95833; 2022-06-05: 1; 2022-06-06: 1; 2022-06-07: 1; 2022-06-08: 1; 2022-06-09: 1; 2022-06-10: 1; 2022-06-11: 1; 2022-06-12: 0.85417
OCS_4.xlsx | OCS -003/(8) TRS - F14 | GK-P527B | C.MY.F14.DD.22.001.2094D | 30318813 | 15 | Description 10 | 0 | 1000 | USD | unit | 1.2 unit/day on 2022/05/01 | 0 | 0
OCS_4.xlsx | OCS -003/(8) TRS - F14 | GK-P527B | C.MY.F14.DD.22.001.2094D | 30318813 | 15 | Description 11 | 0 | 1500 | USD | unit | 0.5 unit/day on end phase 15 | 750 | 0.5 | 2022-03-17: 0.5
OCS_5.xlsx | Tariff - LMP Charges | GK-P527B | C.MY.F14.DD.22.001.2094R | 30318813 | 15 | Description 20 / GK-P527B / C.MY.F14.DD.22.001.2094R | 0 | 1000 | USD | unit | 2 unit/day from 2020/01/01 to 2030/01/01 | 916.6667 | 0.91667 | 2022-03-13: 0.91667
OCS_5.xlsx | Tariff - LMP Charges | GK-P527B | C.MY.F14.DD.22.001.2094D | 30318813 | 15 | Description 20 / GK-P527B / C.MY.F14.DD.22.001.2094D | 0 | 1000 | USD | unit | 2 unit/day from 2020/01/01 to 2030/01/01 | 38104.1667 | 38.1042 | 2022-03-13: 0.10417; 2022-03-14: 2; 2022-03-15: 2; 2022-03-16: 2; 2022-03-17: 2; 2022-03-18: 1.2917; 2022-03-21: 0.22917; 2022-03-22: 2; 2022-03-23: 2; 2022-03-24: 2; 2022-03-25: 2; 2022-03-26: 2; 2022-03-27: 2; 2022-03-28: 2; 2022-03-29: 2; 2022-03-30: 2; 2022-03-31: 2; 2022-04-01: 2; 2022-04-02: 2; 2022-04-03: 2; 2022-04-04: 2; 2022-04-05: 0.47917
OCS_5.xlsx | Tariff - LMP Charges | GK-P527B | C.MY.F14.DD.22.001.2094C | 30318813 | 15 | Description 20 / GK-P527B / C.MY.F14.DD.22.001.2094C | 0 | 1000 | USD | unit | 2 unit/day from 2020/01/01 to 2030/01/01 | 16875 | 16.875 | 2022-04-05: 1.5208; 2022-04-06: 2; 2022-04-07: 2; 2022-04-08: 2; 2022-04-09: 2; 2022-04-10: 2; 2022-04-11: 2; 2022-04-12: 2; 2022-04-13: 1.3542
OCS_5.xlsx | Tariff - LMP Charges | GK-P528C | C.MY.F14.DD.22.001.3094R | 30318813 | 15 | Description 20 / GK-P528C / C.MY.F14.DD.22.001.3094R | 0 | 1000 | USD | unit | 2 unit/day from 2020/01/01 to 2030/01/01 | 41.6667 | 0.041667 | 2022-03-07: 0.041667
OCS_5.xlsx | Tariff - LMP Charges | GK-P528C | C.MY.F14.DD.22.001.3094D | 30318813 | 15 | Description 20 / GK-P528C / C.MY.F14.DD.22.001.3094D | 0 | 1000 | USD | unit | 2 unit/day from 2020/01/01 to 2030/01/01 | 37125 | 37.125 | 2022-03-07: 1.3542; 2022-03-18: 0.70833; 2022-03-19: 2; 2022-03-20: 2; 2022-03-21: 1.7708; 2022-04-13: 0.64583; 2022-04-14: 2; 2022-04-15: 2; 2022-04-16: 2; 2022-04-17: 2; 2022-04-18: 2; 2022-04-19: 2; 2022-04-20: 2; 2022-04-21: 2; 2022-04-22: 2; 2022-04-23: 2; 2022-04-24: 2; 2022-04-25: 2; 2022-04-26: 2; 2022-04-27: 2; 2022-04-28: 0.64583
OCS_5.xlsx | Tariff - LMP Charges | GK-P528C | C.MY.F14.DD.22.001.3094C | 30318813 | 15 | Description 20 / GK-P528C / C.MY.F14.DD.22.001.3094C | 0 | 1000 | USD | unit | 2 unit/day from 2020/01/01 to 2030/01/01 | 21875 | 21.875 | 2022-04-28: 1.3542; 2022-04-29: 2; 2022-04-30: 2; 2022-05-01: 2; 2022-05-02: 2; 2022-05-03: 2; 2022-05-04: 2; 2022-05-05: 2; 2022-05-06: 2; 2022-05-07: 2; 2022-05-08: 2; 2022-05-09: 0.52083
OCS_5.xlsx | Tariff - LMP Charges | GK-W526C | C.MY.F14.DD.22.001.1094R | 30318813 | 15 | Description 20 / GK-W526C / C.MY.F14.DD.22.001.1094R | 1375 | 1000 | USD | unit | 2 unit/day from 2020/01/01 to 2030/01/01 | 13125 | 13.125 | 2022-03-02: 1.375; 2022-03-03: 1; 2022-06-27: 2; 2022-06-28: 2; 2022-06-29: 2; 2022-06-30: 2; 2022-07-01: 2; 2022-07-02: 0.75
OCS_5.xlsx | Tariff - LMP Charges | GK-W526C | C.MY.F14.DD.22.001.1094D | 30318813 | 15 | Description 20 / GK-W526C / C.MY.F14.DD.22.001.1094D | 0 | 1000 | USD | unit | 2 unit/day from 2020/01/01 to 2030/01/01 | 39708.3333 | 39.7083 | 2022-03-03: 1; 2022-03-04: 2; 2022-03-05: 2; 2022-03-06: 2; 2022-03-07: 0.60417; 2022-05-09: 1.4792; 2022-05-10: 2; 2022-05-11: 2; 2022-05-12: 2; 2022-05-13: 2; 2022-05-14: 2; 2022-05-15: 2; 2022-05-16: 2; 2022-05-17: 2; 2022-05-18: 2; 2022-05-19: 2; 2022-05-20: 2; 2022-05-21: 0.6875; 2022-06-12: 0.29167; 2022-06-13: 2; 2022-06-14: 2; 2022-06-15: 2; 2022-06-16: 1.6458
OCS_5.xlsx | Tariff - LMP Charges | GK-W526C | C.MY.F14.DD.22.001.1094C | 30318813 | 15 | Description 20 / GK-W526C / C.MY.F14.DD.22.001.1094C | 0 | 1000 | USD | unit | 2 unit/day from 2020/01/01 to 2030/01/01 | 20354.1667 | 20.3542 | 2022-06-16: 0.35417; 2022-06-17: 2; 2022-06-18: 2; 2022-06-19: 2; 2022-06-20: 2; 2022-06-21: 2; 2022-06-22: 2; 2022-06-23: 2; 2022-06-24: 2; 2022-06-25: 2; 2022-06-26: 2
OCS_5.xlsx | Tariff - LMP Charges | GK-W721C | C.MY.F14.DD.22.001.4094R | 30318813 | 15 | Description 20 / GK-W721C / C.MY.F14.DD.22.001.4094R | 0 | 1000 | USD | unit | 2 unit/day from 2020/01/01 to 2030/01/01 | 83.3333 | 0.083333 | 2022-03-08: 0.083333
OCS_5.xlsx | Tariff - LMP Charges | GK-W721C | C.MY.F14.DD.22.001.4094D | 30318813 | 15 | Description 20 / GK-W721C / C.MY.F14.DD.22.001.4094D | 0 | 1000 | USD | unit | 2 unit/day from 2020/01/01 to 2030/01/01 | 38291.6667 | 38.2917 | 2022-03-08: 1.9167; 2022-03-09: 2; 2022-03-10: 2; 2022-03-11: 2; 2022-03-12: 2; 2022-03-13: 0.97917; 2022-05-21: 1.3125; 2022-05-22: 2; 2022-05-23: 2; 2022-05-24: 2; 2022-05-25: 2; 2022-05-26: 2; 2022-05-27: 2; 2022-05-28: 2; 2022-05-29: 2; 2022-05-30: 2; 2022-05-31: 2; 2022-06-01: 2; 2022-06-02: 2; 2022-06-03: 2; 2022-06-04: 0.083333
OCS_5.xlsx | Tariff - LMP Charges | GK-W721C | C.MY.F14.DD.22.001.4094C | 30318813 | 15 | Description 20 / GK-W721C / C.MY.F14.DD.22.001.4094C | 0 | 1000 | USD | unit | 2 unit/day from 2020/01/01 to 2030/01/01 | 17625 | 17.625 | 2022-06-04: 1.9167; 2022-06-05: 2; 2022-06-06: 2; 2022-06-07: 2; 2022-06-08: 2; 2022-06-09: 2; 2022-06-10: 2; 2022-06-11: 2; 2022-06-12: 1.7083